## GanttChart
[Project Name] Project Schedule
[Company Name]
| Project Start Date | 2021-01-29 |  |  |  | Display Week | 1
Project Lead
Phân tích yêu cầu | Thu thập yêu cầu từ khách hàng | 2024-12-08 | 2024-12-11
Phân tích yêu cầu | Phân tích yêu cầu | 2024-12-08 | 2024-12-11 | START | END | DAYS | % DONE | WORK DAYS
Phân tích yêu cầu | Lập tài liệu đặc tả yêu cầu (SRS) | 2024-12-08 | 2024-12-11
Thiết kế | Thiết kế giao diện người dùng (UI/UX) | 2024-12-18 | 2024-12-24 | 2018-01-29 |  | 5 | 100%
Thiết kế | Thiết kế cơ sở dữ liệu | 2024-12-18 | 2024-12-24 | 2018-02-03 |  | 5 | 60%
Thiết kế | Lập tài liệu kiến trúc phần mềm | 2024-12-18 | 2024-12-24 | 2018-02-08 |  | 4 | 0%
Phát triển | Xây dựng backend (API, xử lý logic) | 2025-01-07 | 2025-01-20 | 2018-02-01 |  | 4 | 75%
Phát triển | Xây dựng frontend (giao diện người dùng) | 2025-01-07 | 2025-01-20 | 2018-02-02 |  | 2 | 50%
Phát triển | Tích hợp frontend và backend | 2025-01-07 | 2025-01-20 | 2018-02-04 |  | 3 | 50%
Kiểm thử | Viết test case | 2025-02-16 | 2025-02-19 | 2018-02-05 |  | 5 | 0%
Kiểm thử | Kiểm thử chức năng | 2025-02-16 | 2025-02-19 | 2018-02-03 |  | 7 | 0%
Kiểm thử | Kiểm thử tích hợp và hiệu năng | 2025-02-16 | 2025-02-19 | 2018-02-10 |  | 7 | 0%
Kiểm thử | Sửa lỗi phát hiện | 2025-02-16 | 2025-02-19
Triển khai và hoàn thiện | Triển khai lên môi trường thực tế | 2025-03-03 | 2025-03-08 | 2018-02-10 |  | 4 | 0%
Triển khai và hoàn thiện | Đào tạo người dùng cuối | 2025-03-03 | 2025-03-08 | 2018-02-14 |  | 3 | 0%
Triển khai và hoàn thiện | Viết báo cáo và bàn giao | 2025-03-03 | 2025-03-08 | 2018-02-14 |  | 3 | 0%
| [Task] |  |  | 2018-02-17 |  | 6 | 0%
| [Task] |  |  | 2018-02-23 |  | 3 | 0%
[Task Category]
| [Task] |  |  | 2018-02-10 |  | 4 | 0%
| [Task] |  |  | 2018-02-14 |  | 3 | 0%
| [Task] |  |  | 2018-02-14 |  | 3 | 0%
| [Task] |  |  | 2018-02-17 |  | 6 | 0%
| [Task] |  |  | 2018-02-23 |  | 3 | 0%
[Task Category]
| [Task] |  |  | 2018-01-29 |  | 1 | 0%
| [Task] |  |  | 2018-01-30 |  | 1 | 0%
| [Task] |  |  | 2018-01-31 |  | 1 | 0%
| [Task] |  |  | 2018-02-01 |  | 1 | 0%
| [Task] |  |  | 2018-02-02 |  | 1 | 0%
TEMPLATE ROWS
See the Help worksheet to learn how to use these rows. You can hide these rows before printing.
[ Level 1 Task or Phase ]
. [ Level 2 Task ]
. . [ Level 3 Task ]
. . . [ Level 4 Task ]
Note on D7: Predecessor Tasks: You can use this column to enter the WBS of a predecessor for reference. The PRO version uses formulas to automatically calculate the Start Date based on the Predecessor.